Project Work Plan

| Component of project (the items below are provided by way of an example, please adjust them according to the structure of your project) | Outputs to be achieved/produced by the end of the implementation of this component | Activities leading to this output | Activity to be started by this date and completed by this date | Partners / Persons involved | Time input (person / days or person / months) |
| --- | --- | --- | --- | --- | --- |
| PHASE ONE |  |  |  |  |  |
| 1. Development of higher education and vocational training issues: recognition and quality assurance of SCHE | National Studies | Data collection and analyses | October 1, 2008 – May, 2009 | International University College, Bulgaria LEIDO, the Netherlands University of Toledo, USA Owens Community College, USA | 3 persons / 45 days 3 persons / 30 days 3 persons / 30 days 3 persons / 30 days |
| 2. Conferences | First International Conference on “Recognition and Quality Assurance of SCHE” | Conference organization: planning, scheduling of activities, call for proposals for presentations from the international community. Participation and presentation of all partners. Structured visits and discussions amongst partnering and other institutions during conference period | October 1, 2008 – June, 2009 | International University College, Bulgaria LEIDO, the Netherlands University of Toledo, USA Owens Community College, USA | 3 persons / 60 days 3 persons / 5 days 3 persons / 5 days 3 persons / 5 days |
| 3. Development of higher education and vocational training issues: recognition and quality assurance of SCHE | Comparative Analysis | Conference results and presentations systematization, analysis; publication preparation, printing and dissemination | June, 2009 – Fall/Winter, 2009 | International University College, Bulgaria | 3 persons / 60 days |
| PHASE TWO |  |  |  |  |  |
| 4. Development of higher education and vocational training issues: Strategic Approaches of SCHE to Addressing Economic and Social Development | National Studies | Data collection and analyses | June, 2009 – Fall/Winter, 2009 | International University College, Bulgaria LEIDO, the Netherlands University of Toledo, USA Owens Community College, USA | 3 persons / 30 days 3 persons / 30 days 3 persons / 45 days 3 persons / 45 days |
| 5. Conferences | Second International Conference on “Strategic Approaches of SCHE to Addressing Economic and Social Development” | Conference organization: planning, scheduling of activities, call for proposals for presentations from the international community. Participation and presentation of all partners. Structured visits and discussions amongst partnering and other institutions during conference period. | June, 2009 – Fall/Winter, 2009 | International University College, Bulgaria LEIDO, the Netherlands University of Toledo, USA Owens Community College, USA | 3 persons / 15 days 3 persons / 5 days 3 persons / 60 days 3 persons / 60 days |
| 6. Development of higher education and vocational training issues: Strategic Approaches of SCHE to Addressing Economic and Social Development | Comparative Analysis | Conference results and presentations systematization, analysis; publication preparation, printing and dissemination | Fall/Winter, 2009 – May, 2010 | University of Toledo, USA Owens Community College, USA | 3 persons / 60 days 3 persons / 60 days |
| PHASE THREE |  |  |  |  |  |
| 7. Development of higher education and vocational training issues: SCHE and Lifelong Learning Systems | National Studies | Data collection and analyses | Fall/Winter, 2009 – May, 2010 | International University College, Bulgaria LEIDO, the Netherlands University of Toledo, USA Owens Community College, USA | 3 persons / 20 days 3 persons / 45 days 3 persons / 30 days 3 persons / 30 days |
| 8. Conferences | Third International Conference on “SCHE and Lifelong Learning Systems” | Conference organization: planning, scheduling of activities, call for proposals for presentations from the international community. Participation and presentation of all partners. Structured visits and discussions amongst partnering and other institutions during conference period. | Fall/Winter, 2009 – May, 2010 | International University College, Bulgaria LEIDO, the Netherlands University of Toledo, USA Owens Community College, USA | 3 persons / 15 days 3 persons / 40 days 3 persons / 5 days 3 persons / 5 days |
| 9. Development of higher education and vocational training issues: SCHE and Lifelong Learning Systems | Comparative Analysis | Conference results and presentations systematization, analysis; publication preparation, printing and dissemination | June, 2010 - Fall/Winter, 2010 | LEIDO, the Netherlands | 3 persons / 20 days |
| PHASE FOUR |  |  |  |  |  |
| 11. Final Phase | Finalizing Feasibility Study on the development of dual/joint SCHE degrees in business and tourism and hospitality management. Finalizing Pilot Plan for SCHE business-related program. Dissemination of findings. | Final visit and discussions at University of Toledo. Dissemination of findings | June, 2010 – Fall/Winter, 2010 | International University College, Bulgaria LEIDO, the Netherlands University of Toledo, USA Owens Community College, USA | 3 persons / 33 days 3 persons / 10 days 3 persons / 10 days 3 persons / 10 days |
| EVALUATION PLAN |  |  |  |  |  |
| 10. Project evaluation plan | Evaluation Reports at all 4 stages of the project | Assessment of research and data collection approach, of conference organization and effectiveness, of comparative publication and feasibility study | Throughout the project period | Dr. Ron Opp, Associate Professor Director of NCSD | 1 person / 30 days |